**"Fruit Garden of Moldova" Project
Procurement Plan for the investment project of the Agro-Industrial College from Riscani**

|  |  |  |
| --- | --- | --- |
| **Procurement Activity** | Will be procured | Estimated tender launch quarter / year |
| **Civil Works** |
| Construction of a didactical laboratory on Processing and quality control of essential oils at Riscani College (~150 sqm) | Works | Q4 2021 |
| **Endowment of the didactical laboratory on Processing and quality control of essential oils** |
| Endowment with oils seeds processing equipment and accessories | Goods | Q4 2021 |
| **Establishing of new oil seeds plantations** |
| Procurement of seedlings for establishment of didactic plantations: 2 ha of lavender and 2 ha of sage | Goods | Q1-Q2 2022 |
| Procurement of horticulture machinery for plantations establishment and maintenance  | Goods | Q1-Q2 2022 |