**"Fruit Garden of Moldova" Project  
Procurement Plan for the investment project of the Technical-Agriculture College from Svetlii**

|  |  |  |
| --- | --- | --- |
| **Procurement Activity** | **Will be procured** | **Estimated tender launch date** |
| **Civil Works and Endowment** |  |  | |
| Construction of a Lab hall (aprox.812 m2) which will contain „Horticulure sorting and packaging lab” and „Agriculture machinery repair and maintenance lab”. (design and supervision) | Works | 2021-2022 |
| Construction of a hangar for agriculture machinery storage (design and supervision). | Works | Q1-Q4 2022 |
| Endowment of students dormitory with furniture and household appliances | Goods | 5-Aug-2020 |
| **Laboratory Equipment** |  |  | |
| Endowment of the „Horticulure sorting and packaging lab” | Goods | Q1-Q4 2023 |
| Endowment of the „Agriculture machinery repair & maintenance lab”. | Goods | Q1-Q4 2023 |
| **Establishing new orchards and Agriculture machinery** |  |  | |
| Establish 3 ha of fruits orchard | Works | Q1-2022 |
| Establish 2 ha of forest/green shelterbelts for the new orchard | Works | Q1-Q4 2022 |
| Weather station for practical lessons | Goods | Q1-Q4 2022 |
| Agriculture machinery with accessories | Goods | Q1-Q4 2021 |