**"Fruit Garden of Moldova" Project
Procurement Plan for the investment project of the Center of Excellence in Viticulture and Winemaking from Stauceni**

|  |  |  |
| --- | --- | --- |
| **Procurement Activity** | **Will be procured** | **Estimated tender launch date** |
| **Civil Works and endowment** |   |  |
| Construction of a "Didactic-experimental Station in Winemaking” (design and supervision) | Works | Q2-Q3 2021 |
| **Endowment of the didactic-experimental Station** |   |  |
| Endowment of vinoteque with accessories for organoleptic classes. | Goods | Q1-Q2 2022 |
| ICT equipment for conference room(s), for organoleptic lab etc. | Goods | Q1-Q2 2022 |
| Wine processing equipment for microwinery laboratory | Goods | Q1-Q2 2022 |
| Fruits processing equipment for horticulture processing laboratory | Goods | Q1-Q2 2022 |
| Furniture for organoleptic appreciation lab | Goods | Q1-Q2 2022 |
| **Agriculture and other machinery** |   |  |
| Agriculture machinery and accessories | Goods | Q1-Q2 2021 |
| **Establish a new vine plantation** |   |  |
| Establish 2ha of vineyard | Works | Q1-Q2 2021 |
| Establish 0.5ha of orchard, including protection fence and irrigation system | Works | Q1-Q2 2021 |